## By People
Person | Question | Week 1: 31 August 2020 - 4 September 2020
|  | Monday (12.45 - 13.40) | Tuesday (13.00- 13.30) | Wednesday (13.00 - 13.15) | Thursday (13.00 - 13.15) | Friday (13.00 - 13.15)
Kim JiHoon (Developer) | What did you do yesterday? | - | I created a placeholder site. | I found shopping plugin for django | I studied userbenchmark site | I did the crawler for cpubenchmark.net.
| What will you work on today? | Create skeleton site and work on DB tables, create crawler | I will work on login/shop module integration. | I will work on the crawler with Benedict | I will intergrate crawler for userbenchmark or cpu/videocardbenchmark. | I am going to settle on the database scheme and sites in order for me and ben ( the other developer) to work together.
| Do you have any obstacles? | No | I need to learn Django for the framework of the website because may take time to learn it. | I have the same difficulties with Benedict | I need to learn django and modelling needs to be done before further customization of website. | The database still not working properly.
Benedict (Developer) | What did you do yesterday? | - | I grabbed the overall data structure of PCSwaps and benchmarking website. | Edited the Items table, added item_category table | Studied the videocardbenchmark site | I did the crawler for videobenchmark.net.
| What will you work on today? | Research on the logic for database creation, Identifying the templates required for the creation of the website and Researching on what is the Crawler and types of libraries that can be used. | I will work on collating the data structure that I did yesterday into objects for the database and model creation. Thus, I will be drawing either a use case diagram or database diagram for visualization. | I am going to work on the crawler with Kim | I am going to finished up the database and do the crawler with Kim | Finalising the Settling on database with the inclusion of materials crawled from both videobenchmark.net and cpubenchmark.net to be converted into sqlite format.
| Do you have any obstacles? | No | I need to familiarize myself in using Django. | Difficulties converting js canvas to actual data points and need to find out whether we need to use js or not | Need to learn django and create models | I am still unfamiliar with django.
Cherry (UI designer) | What did you do yesterday? | - | I began sketching on the design. | Started creating the wireframe | Created wireframe of the website | I have finished up the wireframe.
| What will you work on today? | Sketching the UI | I will create the wireframe of the website. | I will continue making the wireframe | Finish up the wireframe and UI design and start learning about Django | I will start studying on django.
| Do you have any obstacles? | No | I am not familiar with Adobe XD. Therefore, I require more time to get used to it. | Still getting used to Adobe XD | Not familiar with web development | I am not really familiar with how websites work and it may take some time to familiarize.
Michael (Tester) | What did you do yesterday? | - | Manually prepared a small dataset of PC components with appropriate attributes for testing purposes and researched on test plan templates. | Wrote some test cases. | Looked into acceptance testing. | I drafted acceptance test for 'Account Sign Up' user story.
| What will you work on today? | Test plan template and prepare ficticious data. | Start writing test cases. | Learn how to test in Django and find out automated testing tools (for Python code). | I will draft acceptance test for user stories. | I am going to continue drafting acceptance test.
| Do you have any obstacles? | - | Need to learn automated testing tools. | No prior experience in Django and automated testing in Python. | Took some time to understand acceptance testing. | -
Shania (Scrum Master) | What will you work on today? | Looking to the algorithm for the product depreciation and where to get pricing list
Person | Question | Week 2: 7 September 2020 - 11 September 2020
|  | Monday | Tuesday | Wednesday (10.45- 11.05) | Thursday (1.15 - 1.40) | Friday
Kim JiHoon (Developer) | What did you do yesterday? | - | Pushed login function for review | Research on product categories in oscar | Working on product category | Drafted product category
| What will you work on today? | Study database system of e-commerce plugin and talk with ben about exact database scheme | Research on oscar item structure and draft code | Research on oscar item structure and draft code | Continue working on product category | Improve draft and create presentation layer
| Do you have any obstacles? | Learning how to create database models | Learning oscar | Learning oscar | Learning oscar & django | Learning oscar & django
Benedict (Developer) | What did you do yesterday? | - | Updating the item and item_category table to include the unique identifiers. | Learning Oscar, Developing the basic algorithm to lower the cost of computing | Learning oscar and the implementation for Oscar with the special fields in the database | Drafted the required functionalities that need to be expanded from Oscar's standard framework
| What will you work on today? | Finalising the infromation crawled from the various websites and understanding the unique identification of products and item categories | Research on Database to understand what is the models + Crawler CSV strategy to reduce the work load and amount of crawler calls | Research on Database + Crawler CSV strategy | Continue working on expanding the functionalities of Oscar for item crawling | Continue working on Oscar's framework and to create the dashboard interface
| Do you have any obstacles? | Database and crawler | Django | Oscar, Learning Django | Oscar, Learning Django | Oscar, Learning Django
Cherry (UI designer) | What did you do yesterday? | - | Reviewed Python and looked into Django basics | Quick review on HTML and CSS basics | Started creating the home screen while familiarize with bootstrap | Creating the home screen view
| What will you work on today? | Learn about Django framework | Start to try Django and learn aboout bootstrap | Start creating the home screen while learning bootstrap framework | Continue creating the home screen view | Continue and the home screen view and theme
| Do you have any obstacles? | Django | Django | - | - | -
Michael (Tester) | What did you do yesterday? | I drafted acceptance test for 'Account Log In' and 'Account Authentication' user stories. | Finalised the acceptance test template, understood acceptance testing better, wrote some acceptance tests requirements. | Revised acceptance tests, conducted the tests and documented the results. | Explored unit tests using the built-in unittest library. | Wrote some unit testing code for the benchmark crawler function and changed the format of UAT.
| What will you work on today? | Research and figure out a better acceptance test template and understand acceptance testing better. | Continue working on the acceptance tests. | Continue working on the acceptance tests and explore unit tests. | Start working on unit test for the benchmark crawler function and change the format of UAT. | Finish up the unit testing code for the benchmark crawler function.
| Do you have any obstacles? | Misconception on acceptance testing, wrong UAT format. | Difficulties encountered when setting up the test environment and running the local server. | - | Difficulties in understanding unit testing methods. | -
Shania (Scrum Master) | What will you work on today? |  | Looking to the algorithm for the product depreciation and where to get pricing list | - Researching on the drawing information from the js canvas - Difficulties converting js canvas to actual data points and need to find out whether we need to use js or not
Person | Question | Week 3: 14 September 2020 - 18 September 2020
|  | Monday | Tuesday | Wednesday | Thursday | Friday
Kim JiHoon (Developer) | What did you do yesterday? |  | Identified oscar features to create seller function | Identified views and models related to account creation | Forked relevant modules for account registration, creating custom form | Created custom registration form that can register as partner simultaneously
| What will you work on today? | explore how to convert existing oscar system into seller system | customise sign up screen to create user and 'partner' simultaneously | customise sign up screen to create user and 'partner' simultaneously | Add partner creation during registration process | Check new database and finish features with dependency on DB
| Do you have any obstacles? | oscar & django | learning oscar system | learning oscar system | learning oscar & django | learning oscar & django
Benedict (Developer) | What did you do yesterday? |  | Finalising the dashboard interface, finalising the product and item's UI listings (with a basic mockup)
| What will you work on today? | Finalising the dashboard interface, finalising the product and item's UI listings (with a basic mockup) | Continue on yesterday's tasks
| Do you have any obstacles? | Oscar's limitations and ability to modify the source codes | Other subjects requirements is slowing down
Cherry (UI designer) | What did you do yesterday? | Finished the home screen | Finished the product listing view | Start creating product detail view | Creating the product detail view | Creating the product detail view
| What will you work on today? | Product Listing View | Create Product Detail view | Continue product detail view | Finishing up the product detail view | Finishing the product detail view and create the shopping cart
| Do you have any obstacles? | - | - | Confusion about using Django, took a while to fix issue | Difficulties with bootstrap | -
Michael (Tester) | What did you do yesterday? | Partially completed the unit testing code for the benchmark crawler function. | Drafted acceptance test for the 'Add or Remove Items' user story. | Drafted acceptance test for the product types function (website administrator controls). | Drafted acceptance test for the 'List Items' and 'Items Category' user stories. | Revised the unit testing code and included messages as tests may fail with frequent website updates.
| What will you work on today? | Continue working on UAT. | Continue working on UAT. | Continue working on UAT. | Extend the unit testing code for the benchmark crawler function. | Push the benchmark crawler test files into the remote repository on GitHub and continue working on UAT.
| Do you have any obstacles? | - | - | - | Thought of integrating unit tests of django-oscar into the project but could not understand the code well. | Not confident in using Git and its functions such as moving between branches, pushing to a specific branch, comitting files with different commit messages (this is not possible so decided to commit file by file).
Shania (Scrum Master) | What will you work on today?
Person | Question | Week 4: 21 September 2020 - 26 September 2020
|  | Monday | Tuesday | Wednesday | Thursday | Friday
Kim JiHoon (Developer) | What did you do yesterday? |  | Resolved bugs in website template | Checked shopping cart & item search function; filed for testing
| What will you work on today? | Resolve bug that not allows using custom website templates | Work on shopping cart & item search | Integrate dummy payment gateway
| Do you have any obstacles? | django & oscar, unresolved bug | django & oscar | django & oscar
Benedict (Developer) | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Cherry (UI designer) | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Michael (Tester) | What did you do yesterday?
| What will you work on today? | Revised acceptance tests, conducted the tests and documented the results for the 'Add or Remove Items' user story and product types function (website admin controls).
| Do you have any obstacles? | Some difficulties in setting up and running the project and found some errors within the site; consulted with Kim.
Shania (Scrum Master) | What will you work on today?

## By Questions
Question | Person | Week: <date>
|  | Monday | Tuesday | Wednesday | Thursday | Friday
What did you do yesterday? | Jane
Alex
Jessica
What will you work on today? | Jane
Alex
Jessica
Do you have any obstacles? | Jane
Alex
Jessica